REPUBLIC OF KENYA

MINISTRY OF LANDS, PUBLIC WORKS, HOUSING AND URBAN DEVELOPMENT

State Department for Housing and Urban Development

Affordable Housing with Associated Amenities and Infrastructure

PROPOSED CONSTRUCTION OF MAKINDU AFFORDABLE HOUSING PROJECT IN MAKINDU, KIBWEZI WEST CONSTITUENCY, MAKUENI COUNTY WITH ASSOCIATED INFRASTRUCTURE.

MONTHLY REPORT (24th March –

19th April 2026)

- CONTRACT DETAILS

Table 1: Summarized contract information

| 1. | Project Title | Proposed Construction of Makindu Affordable Housing Project in Makindu, Kibwezi West Constituency, Makueni County with associated infrastructure. |
| --- | --- | --- |
| 2. | Contract No. | MLPWHUD/SDHUD/AHP/160/2023-2024. |
| 3. | County | MAKUENI |
| 4. | Sub-County | MAKINDU |
| 5. | Constituency | KIBWEZI WEST |
| 6. | Client | State Department of Housing and Urban Development |
| 7. | Employer | Principal Secretary, State Department of Housing and Urban Development P. O. Box 30119 – 00200 Nairobi, KENYA |
| 8. | Contractor | NETGAS ENERGY AND CONSTRUCTION LTD |
| 9. | Contract Sum | KES. 2,127,050,827.72 |
| 10. | Advance Payment | KES 425,410,165.54 |
| 11. | Commencement Date | 24th November 2025 |
| 12. | Project Duration | 24 Months |
| 13. | Date of Completion | 24th November 2027 |
| 14. | Time Lapsed in Weeks | 21 Weeks |
| 15. | % contract period elapsed | 20.25% |
| 16. | % work done | 7.29% |
| 17. | Reporting Period | 25TH MARCH– 20th APRIL 2026 |

- SOCIO-ECONOMIC IMPACT

The Makindu affordable housing project has significant socio-economic impacts, as it generates employment opportunities during construction and in related supply chains, stimulates local businesses through increased demand for goods and services, and provides secure, decent housing that improves health and safety outcomes for low-income families. By offering rent-to-own and tenant purchase options, it enhances financial stability and asset ownership among residents, while also fostering community development through better infrastructure and social amenities. Overall, the project acts as a catalyst for inclusive economic growth, poverty reduction, and long-term resilience in the region.

- SCOPE OF WORKS

The Works to Be Carried Out Comprises Construction of: -

  - 4 No. Blocks (G+9) Block Type B-Affordable +Market units

  - 5 No. Blocks (G+9) Block type C-Social + Shops + Affordable units

  - Club House (G+1)

  - Kindergarten-(G)

  - Garbage Receptacle

  - Gate House

  - Associated amenities and Infrastructure

The following is a tabulation of items typologies as outlined in the Drawings

| S/N | UNITS | NO. OF UNITS |
| --- | --- | --- |
| 1 | SOCIAL UNITS- 19% |  |
| a). | 1 Room social Housing 20 sqm | 50 |
| b). | 2 Room Social Housing 30 sqm | 100 |
| c). | 3 Room Social Housing 40 sqm | 50 |
| 2 | AHP UNITS- 45% |  |
| a). | Studio Affordable Housing 20 sqm | 100 |
| b). | 2 Bed Affordable Housing 40 sqm | 225 |
| c). | 3 Bed Affordable Housing 60 sqm | 90 |
| 3 | MARKET UNITS- 36% |  |
| a). | 2 Bed Market Housing 60 sqm | 120 |
| b). | 3 Bed Market Housing 80 sqm | 120 |
| 4 | AMENITIES |  |
| a). | Kindergarten |  |
| b). | Shops |  |
| c). | Power House |  |
| d). | Garbage Receptacles |  |
| e). | Gate House |  |
| f). | Playground |  |
| g). | Club House |  |
| h). | Outdoor kids play area |  |
| i). | Secured boundary wall |  |
| j). | Borehole |  |
| k). | back-up Generator |  |
| l). | Cabro paved driveways |  |

- DETAILED SCOPE OF WORKS AND IMPLEMENTATION STATUS

Table 2: Physical work progress executed as at from 24TH Feb 2025 to 23rd March 2026.

GENERAL WORKS

- Construction of 2No. staff Sanitation facilities – done

- Site hoarding branding - ongoing

- 3-phase power connection to site - completed

- Construction of realtor’s office - ongoing

- Installation of CCTV cameras - completed

BUILDER’S WORK

- UNDERGROUND WATER TANK

- Excavation - ongoing

- KINDERGATEN UNIT - Mass excavation and disposal of excavated material within the site – complete - Setting out of the site - Blinding - Rebar installation of the isolated and strip footing - Casting of the footing - Installation of the foundation walling - Hardcore and murram filling and compaction - Casting of ground slab, reinforcement to superstructure columns

- BLOCK TYPE B

B4 - Mass excavation and disposal of excavated material within the site – complete - Blinding works - complete - Rebar to raft foundation and starter columns - complete

B3 - Blinding works - complete - Rebar to raft foundation and starter columns – complete - Casting of raft foundation – complete - Lapping of reinforcement to foundation columns – complete - Setting and casting of columns kickers for the foundation columns – complete - Formwork to lift core – complete

B2 - Blinding works - complete - Rebar to raft foundation and starter columns - complete - Casting of raft foundation – complete - Lapping of reinforcement to foundation columns – complete - Setting and casting of columns kickers for the foundation columns – complete - Formwork to lift core – complete

B1 - Blinding works - complete - Rebar to raft foundation and starter columns - complete - Casting of raft foundation – complete - Lapping of reinforcement to foundation columns – complete - Setting and casting of columns kickers for the foundation columns – complete - Formwork to lift core – done - Formwork to foundation columns – done - Casting of foundation columns and lift core C30 concrete- complete

- BLOCK TYPE C

C5 - Mass Excavation and disposal of excavated material – complete - Blinding works- complete

- INSURANCES

| INSURANCE POLICY | EXPIRY DATE |
| --- | --- |
| Performance security | 15/03/2027 |
| Advance payment guarantee | 02/12/2026 |
| Contractor’s All Risk | 11/03/2027 |
| Public Liability | 02/02/2027 |
| Work Injury Benefit | 02/02/2027 |

- PROGRESS COMPARISON WITH PREVIOUS MEETING

|  | PREVIOUS MEETING | CURRENT MEETING |
| --- | --- | --- |
| Time Elapsed | 16.29% | 20.25% |
| Work Progress | 5.83% | 7.29% |

- CUBES LAB TEST RESULTS DONE TO DATE

| BLOCK B1 BLINDING | Compressive strength at 7 days (N/mm2) |
| --- | --- |
| Sample 1 | 12.3 |
| Sample 2 | 12 |
| Sample 3 | 10.6 |
| BLOCK B1 BLINDING | Compressive strength at 7 days (N/mm2) |
| Sample 1 | 11.1 |
| Sample 2 | 11.9 |

- MACHINES AND EQUIPMENT MOBILIZATION

The following are contractors’ plant and equipment returns reported from 24th Feb to 23rd March 2026.

| Category | No. | Condition | Status |
| --- | --- | --- | --- |
| 21T Chain Excavator | 1 | Good | Working |
| Backhoe excavator | 1 | Good | Working |
| Rotating drum concrete mixers | 2 | Good | Working |
| Batching Plant – 30M3/Hr. | 1 | Good | Working |
| 18-Ton Tipper | 2 | Good | Working |
| Generator | 1 | Good | Working |

| Wheelbarrows | 5 | Good | Working |
| --- | --- | --- | --- |
| Assorted tools and equipment |  | Good | Working |

- LABOUR TURN OVER

In the period under review, the following were number of personnel on site

23rd March –29th March 2026

| CATEGORY | MON | TUE | WED | THU | FRI (Night) | FRI (Day) | SAT | SUN |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Site Agent / PM | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |
| Ass. Site Agent | 1 | 2 | 1 | 1 | 1 | 1 | 1 | 1 |
| Office Attendant / Assistant | 0 | 0 | 3 | 3 | 1 | 0 | 1 | 1 |
| Foreman | 4 | 3 | 4 | 3 | 3 | 3 | 3 | 1 |
| Operator | 8 | 8 | 8 | 4 | 5 | 5 | 5 | 0 |
| Mason | 5 | 5 | 5 | 4 | 2 | 0 | 3 | 0 |
| Electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Carpenters | 9 | 12 | 16 | 10 | 2 | 12 | 7 | 4 |
| Steel Fixers | 9 | 5 | 2 | 2 | 1 | 1 | 8 | 0 |
| Surveyors | 2 | 2 | 2 | 2 | 2 | 0 | 2 | 2 |
| Unskilled (Day) | 31 | 39 | 35 | 37 | 40 | 52 | 42 | 4 |
| Safety Officer | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 |
| Store Keeper | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Security (Day & Night) | 8 | 8 | 2 | 2 | 6 | 2 | 2 | 2 |
| TOTAL | 80 | 88 | 81 | 71 | 64 | 96 | 85 | 19 |

30th March - 5th April 2026

| CATEGORY | Mon | Tue | Wed | Thur | Fri | Sat | Sun |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Site Agent/PM | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Ass. Site Agent | 2 | 2 | 2 | 1 | 1 | 1 | 1 |
| Office Attendant | 0 | 0 | 0 | 1(f) | 2(m) | 2(m) | 2(m) |
| Office Assistant | 0 | 0 | 0 | 2(m) | 1(f) | 1(f) | 1(f) |
| Foreman | 3 | 3 | 3 | 3 | 3(m) | 3(m) | 0 |
| Operator | 5 | 5 | 5 | 4(m) | 4(m) | 6(m) | 0 |
| Mason | 3 | 3 | 3 | 2(m) | 2(m) | 2(m) | 0 |
| Electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Plumbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Carpenters | 0 | 4 | 4 | 1(m) | 4(m) | 1(m) | 0 |
| Steel fixers | 0 | 16 | 16 | 8(1f, 7m) | 1(m) | 1(m) | 0 |
| Steel Unskilled | 0 | 0 | 0 | 7(m) | 1(m) | 0 | 0 |
| Drivers | 0 | 0 | 0 | 0 | 0 | 1(m) | 0 |
| Surveyors | 2 | 2 | 2 | 2(1m, 1f) | 2(1m, 1f) | 2(1m, 1f) | 2(1m, 1f) |
| Unskilled | 15 | 27 | 16 | 6(1f, 5m) | 6(1f, 5m) | 13(3f, 10m) | 1(m) |
| Safety officer | 1 | 1 | 1 | 1(m) | 1(m) | 1(m) | 0 |
| Store keeper | 1 | 1 | 1 | 1(m) | 1(m) | 1(m) | 1(m) |
| Security | 8 | 8 | 8 | 2(1m,1f) | 2(1m, 1f) | 2(1m,1f) | 2(1m, 1f) |
| TOTAL | 41 | 41 | 62 | 42 | 32 | 38 | 11 |

6th April - 12th April 2026

| CATEGORY | Mon | Tue | Wed | Thu | Fri | Sat | Sun |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Site Agent/PM | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Ass. Site Agent | 1 | 2 | 2 | 2 | 1 | 1 | 1 |
| Office Attendant | 1 | 0 | 0 | 0 | 3 | 1 | 1 |
| Office Assistant | 3 | 0 | 0 | 0 | 0 | 3 | 3 |
| Foreman | 1 | 1 | 1 | 1 | 3 | 2 | 1 |
| Operator | 5 | 5 | 6 | 6 | 6 | 6 | 1 |
| Mason | 0 | 4 | 5 | 5 | 3 | 1 | 0 |
| Electrician | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Plumbers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Carpenters | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Steel Fixers | 0 | 0 | 0 | 7 | 8 | 9 | 0 |
| Steel Unskilled | 0 | 0 | 0 | 0 | 4 | 5 | 0 |
| Drivers | 1 | 0 | 0 | 1 | 0 | 0 | 0 |
| Surveyors | 2 | 2 | 2 | 2 | 2 | 2 | 2 |
| Unskilled | 5 | 9 | 9 | 10 | 14 | 11 | 9 |
| Safety Officer | 1 | 1 | 1 | 1 | 1 | 1 | 0 |
| Store Keeper | 1 | 1 | 1 | 1 | 1 | 1 | 1 |
| Security | 2 | 8 | 8 | 8 | 2 | 2 | 2 |
| TOTAL | 24 | 34 | 36 | 45 | 49 | 46 | 22 |

13th April – 19th April 2026

| CATEGORY | Mon | Tue | Wed | Thur | Fri | Sat | Sun |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Site Agent/PM | 1 | 1 | 1 | 1 | 1 | 1(m) | 1(m) |
| Ass. Site Agent | 1 | 1 | 1 | 1 | 1 | 1(m) | 1(m) |
| Office Attendant | 1(f) | 1(f) | 1(f) | 1(f) | 1(f) | 1(f) | 1(f) |
| Office Assistant | 3(m) | 3(m) | 3(m) | 3(m) | 1(m) | 2(m) | 2(m) |
| Foreman | 1(m) | 1(m) | 3(m) | 3(m) | 4(m) | 4(m) | 4(m) |
| Operator | 6(m) | 3(m) | 3(m) | 7(m) | 7(m) | 7(m) | 6(m) |
| Mason | 1(m) | 1(m) | 1(m) | 1(m) | 2(m) | 1(m) | 13(m) |
| Electrician | 0 | 0 | 0 | 0 | 0 | 0 | 1 |
| Plumbers | 0 | 0 | 0 | 0 | 0 | 2 (m) | 2 (m) |
| Carpenters | 0 | 0 | 5(m) | 7(m) | 12(m) | 2(m) | 0 |
| Steel fixers | 0 | 0 | 13(m) 1(f) | 15(14m, 1f) | 13(12m, 1f) | 13(12m, 1f) | 7(m) |
| Drivers | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Surveyors | 2(1f, 1m) | 2(1f, 1m) | 2(1f, 1m) | 2(1f, 1m) | 2(1f, 1m) | 2(1f, 1m) | 2(1f, 1m) |
| Unskilled | 9(1f, 8m) | 10(2f, 8m) | 35(2f, 33m) | 47(9f, 36m) | 45(11f, 34m) | 41(7f, 34m) | 31(6f, 25m) |
| Safety officer | 1(m) | 1(m) | 1(m) | 1(m) | 1(m) | 1(m) | 1(m) |
| Store keeper | 1(m) | 1(m) | 1(m) | 1(m) | 1(m) | 1(m) | 1(m) |
| Security | 2(1m, 1f) | 2(1m, 1f) | 8(7m, 1f) | 8(7m, 1f) | 8(7m, 1f) | 8(7m, 1f) | 8(7m, 1f) |
| TOTAL | 29 | 27 | 81 | 98 | 99 | 88 | 81 |

- MATERIALS DELIVERED TO SITE

| S/N | Description | Total Quantity | Unit |
| --- | --- | --- | --- |
| 01 | D16 Reinforcement Bars | 2,288 | pcs |
| 02 | D20 Reinforcement Bars | 575 | pcs |
| 03 | Cement 32.5N | 580 | bags |
| 04 | Cement 42.5N | 580 | bags |
| 05 | Cement (Unspecified Grade) | 2,030 | bags |
| 06 | Ballast | 453.4 | tons |
| 07 | Aggregates | 338.32 | tons |
| 08 | Foundation Stones | 4674 | ft |
| 09 | Hardcore | 11 | tippers |
| 10 | Clean Fresh Water | 5,000 | Ltrs |

- WEATHER REPORT

23rd March – 30th March 2026

| DAY | MORNING | AFTERNOON | EVENING | CONDITION |
| --- | --- | --- | --- | --- |
| Monday | Cloudy | Cloudy with light showers | Cloudy | Conducive for working |
| Tuesday | Cloudy | Cloudy with light showers | Cloudy | Conducive for working |
| Wednesday | Sunny | Sunny | Cloudy | Conducive for working |
| Thursday | Sunny | Sunny | Cloudy | Conducive for working |
| Friday | Sunny | Sunny | Cloudy | Conducive for working |
| Saturday | Sunny | Sunny | Cloudy | Conducive for working |
| Sunday | Sunny | Sunny | Cloudy | Conducive for working |
|  |  |  |  | Conducive for working |

31st March - 5th April 2026

| DAY | MORNING | AFTERNOON | EVENING | CONDITION |
| --- | --- | --- | --- | --- |
| Sunday | Sunny | Sunny | Cloudy | Conducive for working |
| Monday | Sunny | Sunny | Cloudy | Conducive for working |
| Tuesday | Sunny | Sunny | Cloudy | Conducive for working |
| Wednesday | Sunny | Sunny | Cloudy | Conducive for working |
| Thursday | Sunny | Sunny | Cloudy | Conducive for working |
| Friday | Sunny | Sunny | Cloudy | Conducive for working |
| Saturday | Sunny | Sunny | Cloudy | Conducive for working |
| Sunday | Sunny | Sunny | Cloudy | Conducive for working |

6TH – 12TH March 2026

| DAY | MORNING | AFTERNOON | EVENING | CONDITION |
| --- | --- | --- | --- | --- |
| Monday | Sunny | Sunny | Cloudy | Conducive for working |
| Tuesday | Sunny | Sunny | Cloudy | Conducive for working |
| Wednesday | Sunny | Sunny | Cloudy | Conducive for working |
| Thursday | Sunny | Sunny | Cloudy | Conducive for working |
| Friday | Sunny | Sunny | Cloudy | Conducive for working |
| Saturday | Sunny | Sunny | Cloudy | Conducive for working |
| Sunday | Sunny | Sunny | Cloudy | Conducive for working |

13th -19th March 2026

| Day | Morning | Afternoon | Evening | Condition |
| --- | --- | --- | --- | --- |
| Monday | Sunny | Sunny | Sunny | Conducive for working |
| Tuesday | Sunny | Sunny | Sunny | Conducive for working |
| Wednesday | Sunny | Sunny | Sunny | Conducive for working |
| Thursday | Sunny | Sunny | Sunny | Conducive for working |
| Friday | Sunny | Sunny | Sunny | Conducive for working |
| Saturday | Sunny | Sunny | Sunny | Conducive for working |
| Sunday | Sunny | Sunny | Sunny | Conducive for working |

- HEALTH AND SAFETY

- 3 Minor incidences reported over the reporting period

- SECURITY

- 1 theft case reported

- VISITORS/ CONSULTANTS ON SITE

| S/NO. | NAME | ORGANIZATION | DATE ON SITE | PURPOSE FOR SITE VISIT |
| --- | --- | --- | --- | --- |
| 1. | Teresia Wangui | Medivoly consultants | 24/02/2026 | Site Meeting |
| 2. | Edwin Kariuki | Amazon Consultants | 24/02/2026 | Site Meeting |
| 3. | Mwangi Mwangi | Epoch Consultants (Structural Engineer) | 24/02/2026 | Site Meeting |
| 4. | Paul Bhoyo | Tej Architects (Project Architect) | 24/02/2026 | Site Meeting |
| 5. | Legeck Duncan | Tej Consultants | 24/02/2026 | Site Meeting |
| 6. | Boniface Mule | CDH | 24/02/2026 | Site Meeting |
| 7. | Hellen Chege | DCC | 24/02/2026 | Site Meeting |

- SITE INSTRUCTIONS ISSUED

| REF NO | DETAILS | DATE | INSTRUCTOR |
| --- | --- | --- | --- |
| 019 | MEP Sample Approval – The provided MEP sample board on site has met the requirements. PPR pipes are PN 20, drainage pipes are heavy gauge as per required standards. Electric conduits (metro) & fittings approved. | 24/03/2026 | Tej/Medivolt Consultants |
| 020 | CASTING OF BLINDING (B4) Contractor is given approval to proceed and cast blind for B4 foundation with class 15 of concrete | 02/04/2026 | George Ajwang (Resident Engineer) |
| 022 | CASTING OF BLINDING (C5) Casting of Blind (C5) Contractor is given approval to proceed and cast blind for (C5) foundation with class (15) of concrete. | 15/04/2026 | George Ajwang (Resident Engineer) |

- CHALLENGES

- Mud and water ponding from rain delayed excavation works of foundation pits on certain days

- Untimely mobilization of materials slowing down work progress

- Insufficient tools/equipment used to perform certain activities, causing slow work progress

- PROGRESS PHOTOS

Figure 1: Casting of foundation columns at B1

Figure2: Block B1 with the casted foundation columns

Figure 3: Block B3 raft foundation

Figure 4: Blinding at Block B4

Figure 5: Formwork to raft foundation, Steel fixing and setting of starter columns in Block B4

Figure 6: Excavation of Block C5 foundation pit

Figure 7: Block C5 Foundation pit

Figure 8: Blinding at Block C5

Figure 9: Excavation of pit for the underground tank

Figure 10: Foundation walling construction in the kindergarten building

Figure 11: Kindergarten – hardcore and murram filling and compaction

Figure 12: Kindergarten – casting of ground slab, reinforcement to superstructure columns

Figure 13: Branding of the Site’s Perimeter wall

Prepared by: Grace Musangi

Designation: Clerk of Works

Signature: …………………… Date: ……………………

Signed: ………………………...... Date: ………………….

Lead Consultant (Tej Consortium)