# REPUBLIC OF KENYA

MINISTRY OF LANDS, PUBLIC WORKS,

HOUSING AND URBAN DEVELOPMENT

State Department for Housing and Urban

Development

Affordable Housing with Associated Amenities and

# Infrastructure

PROPOSED CONSTRUCTION OF MAKINDU AFFORDABLE HOUSING PROJECT IN MAKINDU, KIBWEZI WEST CONSTITUENCY, MAKUENI COUNTY WITH ASSOCIATED INFRASTRUCTURE.

# TITLE:

- CONTRACT DETAILS

Table 1: Summarized contract information

| 1. | Project Title | Proposed Construction of Makindu Affordable Housing Project in Makindu, Kibwezi West Constituency, Makueni County with associated infrastructure. |
| --- | --- | --- |
| 2. | Contract No. | MLPWHUD/SDHUD/AHP/160/2023-2024. |
| 3. | County | MAKUENI |
| 4. | Sub-County | MAKINDU |
| 5. | Constituency | KIBWEZI WEST |
| 6. | Client | State Department of Housing and Urban Development |
| 7. | Employer | Principal Secretary, State Department of Housing and Urban Development P. O. Box 30119 – 00200 Nairobi, KENYA |
| 8. | Contractor | NETGAS ENERGY AND CONSTRUCTION LTD |
| 9. | Contract Sum | KES. 2,127,050,827.72 |
| 10. | Advance Payment | KES 425,410,165.54 |
| 11. | Commencement Date | 24th November 2025 |
| 12. | Project Duration | 24 Months |
| 13. | Date of Completion | 24th November 2027 |
| 14. | Time Lapsed in Weeks |  |
| 15. | % contract period elapsed |  |
| 16. | % work done |  |
| 17. | Reporting Period |  |

- SOCIO-ECONOMIC IMPACT

The Makindu affordable housing project has significant socio-economic impacts, as it generates employment opportunities during construction and in related supply chains, stimulates local businesses through increased demand for goods and services, and provides secure, decent housing that improves health and safety outcomes for low-income families. By offering rent-to-own and tenant purchase options, it enhances financial stability and asset ownership among residents, while also fostering community development through better infrastructure and social amenities. Overall, the project acts as a catalyst for inclusive economic growth, poverty reduction, and long-term resilience in the region.

- SCOPE OF WORKS

The Works to Be Carried Out Comprises Construction of: -

- 4 No. Blocks (G+9) Block Type B-Affordable +Market units

- 5 No. Blocks (G+9) Block type C-Social + Shops + Affordable units

- Club House (G+1)

- Kindergarten-(G)

- Garbage Receptacle

- Gate House

- Associated amenities and Infrastructure

The following is a tabulation of items typologies as outlined in the Drawings

| S/N | UNITS | NO. OF UNITS |
| --- | --- | --- |
| 1 | SOCIAL UNITS- 19% |  |
| a). | 1 Room social Housing 20 sqm | 50 |
| b). | 2 Room Social Housing 30 sqm | 100 |
| c). | 3 Room Social Housing 40 sqm | 50 |
| 2 | AHP UNITS- 45% |  |
| a). | Studio Affordable Housing 20 sqm | 100 |
| b). | 2 Bed Affordable Housing 40 sqm | 225 |
| c). | 3 Bed Affordable Housing 60 sqm | 90 |
| 3 | MARKET UNITS- 36% |  |
| a). | 2 Bed Market Housing 60 sqm | 120 |
| b). | 3 Bed Market Housing 80 sqm | 120 |
| 4 | AMENITIES |  |
| a). | Kindergarten |  |
| b). | Shops |  |
| c). | Power House |  |
| d). | Garbage Receptacles |  |
| e). | Gate House |  |
| f). | Playground |  |
| g). | Club House |  |
| h). | Outdoor kids play area |  |
| i). | Secured boundary wall |  |
| j). | Borehole |  |
| k). | back-up Generator |  |
| l). | Cabro paved driveways |  |

- WORK DONE UPTO DATE

| SUMMARY OF WORK DONE TO DATE: |  |
| --- | --- |
| GENERAL WORKS | - Hoarding - Construction of site office - Construction of Cement store - Construction of general store - Construction of Operation room for the batching plant - Construction of Ablution blocks - Construction of changing rooms (male and female) - Electrical power connection - CCTV installation - WIFI installation - Borehole drilling - 3-phase power connection - Construction of realtor’s office |
| BLOCK B1 | - Site clearance - Setting out - Mass excavation ongoing - Compaction of excavated section - FDD Test - Blinding works - Reinforcement to the raft foundation - Casting of raft foundation- done - Reinforcement and formwork of foundation columns and lift shear wall - Formwork to starter columns and lift shear wall. |
| BLOCK B2 | - Site clearance - Setting out - Excavation for raft foundation to a depth of 3m. - Levelling and compaction. - FDD Test - Blinding works - Reinforcement to the raft foundation - Casting of raft foundation- done - Reinforcement of foundation columns and lift shear wall - Formwork of the lift shear wall - ongoing |
| BLOCK B3 | - Site clearance - Setting out - Excavation for raft foundation to a depth of 3m. - Levelling and compaction. - FDD Test - Blinding works - Reinforcement to the raft foundation 4 - Casting of raft foundation- done - Reinforcement of foundation columns and lift shear wall |
| BLOCK B4 | - Site clearance - Setting out - Excavation for raft foundation to a depth of 3m - ongoing. |
| UNDERGROUND TANK | - Site clearance - Setting out - Excavations for the foundation pit. - Other works on hold |
| KINDERGATEN | - Site clearance - Excavation for pad footings and trenches for strip footing. - Levelling and compaction. - Concrete blinding. - Casting of strip and pad footings. - Casting of substructure columns. - Foundation walling -ongoing |
| SWIMMING POOL | - Site clearance - Setting out. - Other works on hold |
| CLUB HOUSE | • None |
| SEPTIC TANK | • None |
| WASTE CUBICLE | • None |
| WTP | • None |

- INSURANCES

| INSURANCE POLICY | EXPIRY DATE |
| --- | --- |
| Performance security | 15/03/2027 |
| Advance payment guarantee | 02/12/2026 |
| Contractor’s All Risk | 11/03/2027 |
| Public Liability | 02/02/2027 |
| Work Injury Benefit | 02/02/2027 |

- CUBES LAB TEST RESULTS DONE TO DATE

| BLOCK B1 BLINDING | Compressive strength at 7 days (N/mm2) |
| --- | --- |

MACHINES AND EQUIPMENT MOBILIZATION

| Category | No. | Condition | Status |
| --- | --- | --- | --- |
| Excavator | 1 | Good | Working |
| Backhoe excavator | 1 | Good | Working |
| Rotating drum concrete mixers | 2 | Good | Working |
| Batching Plant – 30M3/Hr. | 1 | Good | Working |
| 18-Ton Tipper | 2 | Good | Working |
| Generator | 1 | Good | Working |
| Wheelbarrows | 5 | Good | Working |
| Assorted tools and equipment |  | Good | Working |

- LABOUR TURNOVER

In the period under review, the following were number of personnel on site

- MATERIALS DELIVERED TO SITE

- WEATHER REPORT

K. HEALTH AND SAFETY

L. SECURITY

  - VISITORS/ CONSULTANTS ON SITE

| S/N | NAME | ORGANISATION | DATE ON SITE |
| --- | --- | --- | --- |
| 1. |  |  |  |
| 2. |  |  |  |
| 3. |  |  |  |

  - SITE INSTRUCTIONS ISSUED

## O. CHALLENGES

## PROGRESS PHOTOS

### Block B1

Block B2

### A view of Block B3

### A view of Block B4

Realtor’s office

### Foundation walling – Kindergarten

Prepared by: Grace Musangi

Designation: Clerk of Works